Terug naar Ingelse & Cath

# TWINNING  INTERIM QUARTERLY REPORT number: Three

# EUROPEAN COMMISSION

# TWINNING PROJECTS

# INTERIM QUARTERLY REPORT

# Project Title: Support to the establishment of Courts of Appeal in the Republic of Turkey

# Partners:  Ministry of Justice of the Republic of Turkey and the Netherlands Council for the Judiciary and the Swedish National Courts Administration

Date: November 2006

Section 1: Project data

| Twinning Contract Number | TR 2004/IB/JH-01 |
| --- | --- |
| Project Title: | Support to the establishment of Courts of Appeal in the Republic of Turkey |
| Twinning Partners (MS and BC) | Netherlands Ministry of Justice (administrative authority) in cooperation with the Netherlands Council for the Judiciary (implementing authority) as leading MS and the Swedish National Courts Administration Junior MS. The Ministry of Justice of the Republic of Turkey |
| Report Number: | Three |
| Period covered by the report: | 19 July 2006 – 18 October 2006 |
| Duration of the project: | 18 months |
| Rapporteur: | Mr. A.H. van Delden |

Section 2: Content

2A – BACKGROUND

2B – ACHIEVEMENT OF MANDATORY RESULTS

2C – ACTIVITIES IN THE REPORTING PERIOD

2D – TIMING AND DELAYS

2E – ASSESSMENT

2A - BACKGROUND

Policy Developments

- What were the key developments in the relevant policy area in the BC in the reporting period?

In IQR 1 and 2 we already mentioned the related project on the construction of three model courts of appeal. When writing this report, the tender process is in its final stage: the company that will carry out the construction will be selected soon and the construction will start early November 2006 (information EC Delegation). Again we note that these model courts will not be available before September 2008, while all courts of appeal have to open their doors as from 1 June 2007.

Unfortunately we have to reiterate that we still are looking forward to the necessary steps as recommended in the first and second IQR like definitely deciding upon the number of Courts of Appeal, their seats and jurisdiction, making necessary appointments and drafting necessary Bylaws. Of course, only two months expired between this report and the previous one and even less between the last PSC meeting and this report. However, as from 1 November 2006 until 1 June 2007 only seven months remain. We assume that the Turkish authorities persist in their intention, as determined by law, to open the courts on 1 June 2007. The RTA had the honour to visit the Vice-President of the High Council for Judges and Prosecutors just before finishing the draft of this report. The Vice-President shared our opinion that preparatory concrete steps (buildings, infrastructure etc) should be taken very soon.

We cannot but repeat our recommendations in IQR 1 and 2. We come back to this later in this report.

Project Assumptions

- Which of the original assumptions of the project (Article 2 of the Work plan) have been fulfilled?

- Which of them are likely to be fulfilled soon?

- Have there been any developments, which make some of the assumptions impossible to achieve? (If yes, the project requires reorientation)

The following assumptions are mentioned in article 3 of the Workplan.

|  | Assumptions | Status quo IQR1 | Status quo IQR 2 | Status quo IQR 3 |
| --- | --- | --- | --- | --- |
| Overall objective | Continued political support for the reform of the judiciary by the Ministries, the Parliament and the Court of Cassation Support and commitment from all stakeholders within the judiciary and in particular the Court of Cassation Availability of financial resources in order to cover all needs of the newly established courts Support and commitment of High Council for Judges and prosecutors. Where the appointment and establishment delays, the Republic of Turkey shall train all the prospective judges, prosecutors and auxiliary personnel | See below | See below | See below |
| Project purpose | Continued political support by Ministries, the Parliament and the Court of Cassation for the reform of the judiciary and the quick establishment and effective functioning of the Courts of Appeal Judges, prosecutors and auxiliary personnel for the Courts of Appeal appointed on time by the High Council for Judges and Prosecutors and available to participate in the activities of the project and in particular in the training | See below | See below | See below |
| Mandatory results | The High Council for Judges and Prosecutors selects and appoints judges and prosecutors and auxiliary personnel timely Involvement and support of the Justice Academy Continued political support by the Ministries, the Parliament and the Judiciary Continued support of the Stakeholders, including the judges and prosecutors of the Court of Cassation Active involvement of judges and prosecutors in training Sufficient finances and human resources allocated by the Turkish government | See below | See below | See below |
| Kick off meeting | Turkish authorities support the informing of the public at large about the reform of the judicial system | + | + | + |
| Component 1 | Commitment of the judges and prosecutors of the Court of Cassation and their availability to attend the conferences | + | + | + |
| Component 3 | Judges and prosecutors appointed on time. The Ministry of Justice will take care of the extra training activities. Support of the TtT approach both by the ministry and the stakeholders Criteria for trainers (qualifications, experience in training etc) are elaborated and ready on time | See below | See below | See below + + |
| Component 3 Block B | Trainers timely identified Future trainers committed to be trained and to later train their colleagues in CoA and co-operate with the Justice Academy High Council for Judges and Prosecutors appoints the judges, prosecutors and auxiliary staff for the Courts of Appeal before the start of the training. High Council for Judges and Prosecutors releases judges and prosecutors and auxiliary personnel will be released for training Judges, prosecutors and auxiliary personnel will absorb the training Support and commitment of High Council for Judges and prosecutors | See below | See below | + + See below |
| Component 4 | Influential officials being selected and available for the visit | + | + | + |
| Component 4 activity 4.1 | Officials being committed to technically take profit of the visit to better understand the Appeal System in NL and FR and use their impressions in adjusting the introduced system in Turkey | + | + | + |
| Round up of the project | Participation of stakeholders to the conference Participation of media to the press conference | See below | See below | See below |

Comments

Our recommendations in IQR 1 and IQR 2 (2A) are well known, so we will repeat them at the end of this report only.

It appears that – as far as we are informed and apart from the appointment of BC trainers for the trainings – again hardly anything has been done to meet these recommendations during the third project quarter. We consider it of high importance that the Turkish authorities show the political will to implement the law and carry out the many preparation tasks to establish strong and adequately operating Courts of Appeal. This is also of high interest for the project: the actual trainings will start in the beginning of next year. If by then no progress has been made, we risk that the necessary commitment of experts, trainers and trainee’s to make the training program a success will be affected.

2B - ACHIEVEMENT OF MANDATORY RESULTS

- List all the benchmarks which were achieved in the reporting period within each of the components and indicate which of the Intermediate Results and Mandatory Results are completed or close to completion.

| Benchmarks | Ready by month | Status quo IQR1 | Status quo IQR 2 | Status quo IQR 3 |
| --- | --- | --- | --- | --- |
| COMPONENT ONE: Conferences for Judges and Prosecutors of the Court of Cassation |  |  |  |  |
| Component Benchmarks achieved: |  |  |  |  |
| Agendas and material for first conference prepared |  | + | + | + |
| One conference carried out |  | See 1.2 | Will be finished in September | Will be finished in October |
| Activity Benchmarks achieved: |  |  |  |  |
| 1.1 Agenda of the conference finalized | 2 | + | + | + |
| 1.2 Conference carried out and documentation thereof disseminated | 3 | Conference carried out, but documents not yet disseminated. Some translations not yet finished and the draft report with recommendations still has to be determined. | Will be finished in September | Will be finished in October |
| 1.3 Publication and dissemination of the speeches and a summary of the discussion at the first conference | 6 |  | Will be finished in September (some translations are pending) | Will be finished in October |
| 1.7 Recommendations of the first conference gathered and forwarded to the relevant persons within the Ministry of Justice | 6 |  | + (the final version has yet to be translated) | + |
| COMPONENT TWO: Preparation of handbooks for the Courts of Appeal |  |  |  |  |
| Component Benchmarks achieved: |  |  |  |  |
| None yet |  |  |  |  |
| Activity Benchmarks achieved: |  |  |  |  |
| 2.1 Assessment report with findings and recommendations regarding Civil Procedure handbook content ready | 2 | + | + | + |
| 2.2 Agreed table of content for Civil Procedure handbook and plan of action with tasks’ division prepared | 3 | + | + | + |
| 2.3 A draft handbook ready and submitted for comments to the BC stakeholders | 5 |  | + (August 2006) | + |
| 2.4 First complete version of handbook ready, 3000 copies of handbook printed and disseminated | 9, 13 |  |  | Third meeting of the working group on the preparation of civil handbook focused on review of the complete version of the handbook, some amendments to be draft by MS experts were suggested. These have been received in October. After acceptation by BC experts and translation, the first complete version of the handbook be ready by project month 11. |
| 2.5 Assessment report with findings and recommendations regarding Criminal Procedure handbook content ready | 2 | + | + | + |
| 2.6 Agreed table of content for Criminal Procedure handbook and plan of action with tasks’ division ready | 3 | + | + | + |
| 2.7 A draft handbook ready and submitted for comments to the BC stakeholders | 5 |  | + (August 2006) | + Comments from the Bar Association are received; no other comments from any other stakeholders are received. Decision on possible amendments yet to be taken. |
| 2.8 First complete version of handbook ready, 6000 copies of handbook printed and disseminated | 9, 12 |  |  | Third meeting of the working group on the preparation of criminal handbook was convened to review the final version of the handbook. Some amendments were recommended and applied on the book in early October. As the amendments made were not indicated, twinning team is working to identify amendments in the latest Turkish version so that the English version is harmonized accordingly. The first complete version of the handbook is expected to be ready by the end of October. |
| 2.9 Joint methodology and content for the handbooks agreed on by the different working groups | 3 | + | + | + |
| 2.10 Assessment report with findings and recommendations regarding Auxiliary personnel handbook content ready | 3 | + | + | + |
| 2.11 Agreed table of content for Auxiliary personnel handbook and plan of action with tasks’ division ready | 4 | + | + | + |
| 2.12 A draft handbook ready and submitted for comments to the BC stakeholders | 6 |  | + | + |
| 2.13 First complete version of handbook ready, 150 copies of handbook printed, agenda of evaluation workshop ready | 8 |  | + The biggest part of the final version of the handbook has been completed. Just the general part (compilation of general parts civil and criminal handbook) has to be inserted. Except for the general part, the handbook is ready for translation. The agenda of the evaluation workshop is ready. | + The missing parts of this handbook in the second reporting period were completed in the third reporting period. Newly added parts are also translated and integrated to the former translation of the handbook. The efforts of the twinning team to harmonize both translations and increase the quality of the English translation of the handbook is still going on. |
| 2.14 Evaluation report on handbook ready, amendments of handbook incorporated, 2000 copies of handbook ready for dissemination | 11 |  |  | Evaluation meeting was carried out in October. Participants had all reviewed the book at length and thus fruitful discussions took place in the evaluation meeting. The report of this meeting and incorporation of amendments to the handbook are expected to be done in the shortest possible time, assignments of these duties are done. |
| COMPONENT THREE: Training of Judges, Prosecutors and Auxiliary personnel of the Courts of Appeal |  |  |  |  |
| Component Benchmarks achieved: |  |  |  |  |
| TNA for judges and prosecutors performed Course on Civil Procedure for Judges developed Course on Criminal Procedure for Judges and Prosecutors developed Course on Case-flow management for Auxiliary personnel developed |  | + | + + + + + | + + + + + |
| Activity Benchmarks achieved: Block A |  |  |  |  |
| Training needs analysis and development of training courses |  | + | + | + |
| 3.1 TNA for judges and prosecutors executed, experts’ report with recommendations on topics ready | 4 | + | + | + |
| 3.2 Minutes of meeting, record of course content and methodology, record of background material, ready | 5 |  | + | + |
| 3.3 First draft of the course, including plan of content, methodology and record of gathered information ready | 6 |  | + | + |
| 3.4 Course (final version) ready | 8 |  | + Some of the background material still has to be gathered and translated. | + In the third reporting period the remaining tasks of 3.4 are completed. |
| 3.5 Minutes of the meeting, record of course content and methodology, record of background material ready | 5 |  | + | + |
| 3.6 First draft of the course, including plan of content, methodology and record of gathered information, ready | 6 |  | + | + |
| 3.7 Course (final version), ready | 8 |  | + Some of the background material still has to be gathered and translated. | Some of the background material still has to be translated |
| 3.8 An in-service training provision for judges and prosecutors | 11 |  |  | + Recommendations ready in draft. Yet to be approved by BC experts. |
| 3.9 TNA for auxiliary personnel executed, experts’ report with recommendations on topics ready | 5 | + | + | + |
| 3.10 Minutes of the meeting, record of course content and methodology, record of background material, ready | 6 |  | + | + |
| 3.11 First draft of the course curriculum, including plan of content, methodology and record of gathered information, ready | 7 |  | + Course curriculum is ready. Background material for the course is decided upon. Some translation work remains on the Handbook for auxiliary personnel. | + Remaining translation task is completed in the third reporting period. |
| 3.12 Course (final version), ready | 8 |  | + The benchmark was reached after the second meeting of the working group, so the third meeting (3.12) was skipped. | + |
| 3.13 An in-service training provision for auxiliary personnel ready | 11 |  |  | + Recommendations ready in draft. Yet to be approved by BC experts. |
| Block B: |  |  |  |  |
| Train the Trainers |  |  |  |  |
| 3.21 Curriculum for TtT developed according to course curriculum, training in didactics conducted | 11 |  |  | + |
| Block C: |  |  |  |  |
| Training programme |  |  |  |  |
| Not yet |  |  |  |  |
| COMPONENT FOUR: Acquainting Turkish officials from the Ministry of Justice and the Justice Academy with the Appeal System in EU MS |  | + | + | + |
| Component Benchmarks achieved: |  |  |  |  |
| Participants of study visit acquainted with judicial systems in NL and France |  | + | + | + |
| Activity Benchmarks achieved: |  |  |  |  |
| 4.1 A 10-day Study Visit for 10 Turkish officials to the NL and FR completed, evaluated and reported | 3 | Visit completed, report will follow soon. | 4.1 Report of study visit finished (July) | + |
| 4.1 Basis for courts network for future contacts and collaboration established |  | See report | + | + |

2C. ACTIVITIES IN THE REPORTING PERIOD

- Component by component, list all the activities which have taken place in the reporting period in the order in which they appear in the Work plan and providing their reference numbers.

- For each activity specify the following details:

(1) Reference number and title of Activity (as in Art 3 of the Work plan);

(2) Names of MS experts who delivered it;

(3) Number of experts from the BC who participated and their departments of origin

(4) Duration of the activity

We have attached the activity reports of all activities in the reporting period.

Component one: Conferences for Judges and Prosecutors of the Court of Cassation

Component two: Preparation of handbooks for the Courts of Appeal

Activity 2.4 Third Meeting of the Working Group on the preparation of a Civil Appeal Procedure Handbook for Judges

Duration: Two days ( 28-29 September 2006)

Participants MS

- Mr. Bertil Ahnborg: Judge at the Svea Court of Appeal, Sweden;

- Mr. Jean-Jacques Heintz: Resident Expert for the Council of Europe, France;

- Mr. Frank Hovens: Law Clerk at the Court of Appeal Arnhem, Netherlands.

- Mr Peter Ingelse, Vice President Court of Appeal Amsterdam/RTA

Participants BC

- Mrs. Mine Kaya: Reporter Judge at the Yargitay (afternoon) ;

- Mr. Adem Aslan: Ankara Judge (afternoon);

- Mr. Osman Çalişkan: Reporter Judge at the General Directorate of Laws;

- Doç. dr. Muhammed Özekes, Dokuz Eylül University;

- Mr. Celallatin Dönmez, RTA Counterpart, Reporter Judge at the Ministry of Justice

Activity 2.8

Third meeting of the working group on the preparation of a criminal procedure Handbook for Judges in Courts of Appeal

Duration: Three days (6 - 8 September 2006)

Participants MS

- Bertil Ahnborg, Judge of Appeal, Svea Court of Appeal

- Irene de Vries, Vice-president and Justice, Court of Appeal, Amsterdam, component leader

- Peter Ingelse, Vice President Court of Appeal Amsterdam/RTA

Participants BC

- Ulvi Altinisik, Reporter Judge at the Ministry of Justice, Component Leader

- Abdi Cengiz, Public Prosecutor of Sincan

- Cemal Dönmez, Public Prosecutor of Ankara,

- Yüksel Erdogan, Reporter Judge at the General Directorate of Laws

- Murat Esen, Public Prosecutor of Ankara,

- Hasan Tahsin Göksan, Reporter Judge at the Court of Cassation

- Hüseyin Görüsen, Public Prosecutor of Ankara

- Beytullah Metin, Reporter Judge at the 6th Criminal Division of the Court of Cassation

- Prof. Dr Bahri Öztürk, Istanbul Culture University

- Salih Sönmez, Judge from Sincan

- Prof. Dr Dogan Soyaslan, Baskent University and High Adviser of the Ministry

Activity 2.14 Evaluation workshop regarding handbook auxiliary personnel

Duration: Two days (12 and 13 October)

Participants MS

- Lars Dahlstedt, Chief judge (President of the Court) (SE)

- Helena Jönrup-Nilsson, Specially qualified secretary at the Court of Appeal for Western Sweden (SE

- Jolanda Hussain-Hendriks, Senior employee at the office of the Public Prosecution Service at the Court of Appeal in The Hague (NL)

- Julia Horzinek, Public Prosecutor at the Court of First Instance in Haarlem (NL

- Åsa Toll, Associate Judge of Appeal, Senior Legal Advisor at the Swedish National Courts Administration (SNCA) (SE)

Participants BC

- Enver Özdemir, Eskisehir/ Sivrihisar, Head of Clerks

- Selman Atmaca, Denizli, Head of Clerks

- Yasin Akaya, Eskisehir, Head of Clerks

Component three: Training of Judges, Prosecutors and Auxiliary personnel of the Courts of Appeal

Activity 3.8 Design an in-service training provision for judges and prosecutors

Duration: Three days (20 – 22 September 2006)

Participants MS

- Antoinetta J.M.E. Arpeau, Vice-President Court of Appeal The Hague (NL)

- Piet Hein A.J. Cremers, Chief Public Prosecutor Court of Appeal `s-Hertogenbosch (NL)

- Peter Ingelse, Vice president Court of Appeal in Amsterdam and Resident Twinning advisor.

Participants BC

- Mustafa Albayrak, Reporter Judge at the Yargıtay

- Muzaffer Bayram, General Directorate of Penal Affairs, Reporter Judge

- Osman Caliskan, General Directorate of Legislation, Reporter Judge

- Fazlı Doğan, General Directorate of International Law and Foreign Affairs, Head of Chamber

- Ulvi Altınışık, General Directorate of European Union, Reporter Judge

Activity 3.13 Design an in-service training provision for auxiliary staff

Duration: Three days (25 – 27 September 2006)

Participants MS

- Peter Ingelse, Vice president Court of Appeal in Amsterdam and Resident Twinning advisor

- Helena Jönrup-Nilsson, Specially qualified secretary at the Court of Appeal for Western Sweden (SE

- Majella Vriend, Legal Clerk at the Court of Appeal in Arnhem (NL)

Participants BC:

- Hakan Atasoy,  Reporter Judge at the IT Department of the Ministry of Justice

- Unal Bozdag, Reporter Judge at the Training Department of the Ministry of Justice

- Orhan Kirman, Chief Clerk at the Ankara Court House

- Huriye Kumcu, Chief Clerk at the Justice Commission at the Sincan Court House

Activity 3.21 First intensive seminar on case-flow management for auxiliary personnel

Duration: Three days (13 -15 September 2006)

Participants MS

- Nga Yau Wong, Legal Clerk, Court of Appeal Amsterdam

- Peter Sundström, Judge, Linköping District Court, Sweden

- Kicki Sundelin, Pedagogy expert, temporary employee of SNCA, Sweden

- Lars Dahlstedt, Chief Judge, Norrköping District Court, Sweden

Participants BC:

- Enver Özdemir, Eskisehir/ Sivrihisar, Head of Clerks

- Selman Atmaca, Denizli, Head of Clerks

- Yasin Akaya, Eskisehir, Head of Clerks

2D. TIMING AND DELAYS

Adherence to time schedule

Reproduce the Schedule from Article 4 of the Work plan and indicate with a cross in the relevant box all the activities which have taken place from inception of the project until the end of the reporting period.  In this way the reader will see a clear picture of the delays.

Single out those activities which are delayed by more than three months.

|  | Activity planned |
| --- | --- |
| X | Activity performed |
|  | Activity delayed by more than 3 months |

| Project Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Inception of the project |
| Kick-off meeting of the project | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 1 Conferences for judges and Prosecutors of the Court Of Cassation |
| Activity 1.1 Preparation of the agenda for the first conference | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.2 First Conference for judges and prosecutors of the CofC |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity1.3 Publication and dissemination of the first conference |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.4 Preparation of the agenda for the Second conference |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.5 Second conference for judges and prosecutors of the CofC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.6 Publication after second conference |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.7 Gathering recommendation of the conferences |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component Result |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | C1 R |

| Project month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Component 2 Preparation of Handbooks for The Courts of Appeal |
| Activity 2.1 Gathering of information and background material concerning civil procedure | X |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.2 First meeting of the WG on Civil Procedure Handbook for Judges in CoA |  | X |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.3 Second meeting of the WG on Civil Procedure Handbook for Judges in CoA |  | X |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.4 Third meeting of the WG on Civil Procedure Handbook for Judges in CoA |  |  |  |  | Postponed |  |  |  | x |  |  |  |  |
| Activity 2.5 Gathering of information and background material concerning criminal procedure | X |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.6 First meeting of the WG on Criminal Procedure Handbook for judges and prosecutors |  | X |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.7 Second meeting of the WG on Criminal Procedure Handbook for judges and prosecutors |  | X |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.8 Third meeting of the WG on Criminal Procedure Handbook for judges and prosecutors |  |  |  |  | Postponed |  |  | X |  |  |  |  |  |
| Activity 2.9 Joint meeting of the Working Groups on Civil and Criminal Procedures |  | X |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.10 Gathering of information on case-flow management and work processes in Turkish courts | X |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.11 First meeting WG on handbook for auxiliary personnel |  | X |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.12 Second meeting WG on handbook for auxiliary personnel |  |  |  | X |  |  |  |  |  |  |  |  |  |
| Activity 2.13 Third meeting WG on handbook for auxiliary personnel |  |  |  |  | X |  |  |  |  |  |  |  |  |
| Activity 2.14 An evaluation workshop regarding the handbook for auxiliary personnel |  |  |  |  |  |  |  |  | X |  |  |  |  |
| Component Result |  |  |  |  |  |  |  |  |  |  |  |  | C2 R |

| Project Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Component 3 Training of judges, prosecutors And auxiliary personnel of CoA |
| Block A TNA and development training courses |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.1 TNA for judges and prosecutors |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.2 1st meeting on the course Civil Procedure for judges |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.3 2nd meeting on the course Civil Procedure for judges |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.4 3 rd meeting on the course Civil Procedure for judges |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.5 1st meeting on the Course Criminal Procedure for judges and prosecutors of the CoA |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.6 2nd meeting on the Course Criminal Procedure for judges and prosecutors of the CoA |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.7 3rd meeting on the Course Criminal Procedure for judges and prosecutors of the CoA |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.8 Design an an-service training provision for judges and prosecutors of the CoA |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |
| Activity 3.9 TNA for auxiliary personnel |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.10 First meeting of the WG on the course case-flow management for auxiliary personnel of the CoA |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.11 Second meeting of the WG on the course case-flow management for auxiliary personnel of the CoA |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.12 Third meeting of the WG on the course case-flow management for auxiliary personnel of the CoA |  |  |  |  |  |  | Annulled |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.13 Design an in-service training provision for auxiliary personnel of the CoA |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |

| Project Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Block B Train the trainers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.14 First intensive seminar on civil procedure for future trainers of judges |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.15 Second intensive seminar on civil procedure for future trainers of judges |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.16 Third intensive seminar on civil procedure for future trainers of judges |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.17 First intensive seminar on criminal procedure for future trainers of judges and prosecutors |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.18 Second intensive seminar on criminal procedure for future trainers of judges and prosecutors |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.19 Third intensive seminar on criminal procedure for future trainers of judges and prosecutors |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.20 Study visit of the future trainers of judges and prosecutors to the Netherlands |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.21 First intensive training seminar for future trainers of auxiliary personnel |  |  |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |
| Activity 3.22 Second intensive training seminar for future trainers of auxiliary personnel |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.23 Third intensive training seminar for future trainers of auxiliary personnel |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.24 Study visit of the future trainers of the auxiliary personnel to Sweden |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Project Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Block C Training programme |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.25 Ten Training seminar for judges dealing with civil cases |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.26 Fourteen seminars for judges dealing with criminal cases and prosecutors |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.27 Twelve seminars for auxiliary personnel |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component Result |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | C3 R |

| Project Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Component 4 Acquainting Turkish officials with Appeal system in EU MS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 4.1 Study visit of Turkish Officials to NL and SE |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component Result |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Recuperation of delays

For all the activities marked in the schedule as delayed by more than three months, provide an explanation of the delay and indicate when the activities will take place.

First conference of Judges and Prosecutors of the Court of Cassation

The publishing of a booklet and the report of recommendations under activity 1.2, 1.3 and 1.7 (First conference of Judges and Prosecutors of the Court of Cassation) have not yet been finalized. They are not finished yet and – opposed to what we mentioned in IQR 2 – are not completely ready for translation yet. Finalizing is expected in November.

Conclusion

- The publishing of a booklet and the report of recommendations under activity 1.2, 1.3 and 1.7 (First conference of Judges and Prosecutors of the Court of Cassation) still have not been finalized. Now this is expected for November.

No further delay has occurred.

2E. ASSESSMENT

Overall Assessment of progress

Overall evaluation of the progress achieved during the reporting period.

The project is still running well. Due to holiday time relatively few activities were organized. In the reporting period the following activities took place:

- 4 Working group meetings and 1 evaluation workshop, each 2-3 days, all devoted to the preparation of handbooks and the design of in service trainings

- 1 Train the Trainers seminars on case flow management for the auxiliary personnel

The BC and MS experts continued to work on the civil and criminal handbooks for judges (and prosecutors) and the handbook for auxiliary personnel. These handbooks are almost finalized. Except for one reply by the Bar Association we did not receive any comments from stakeholders.

Recommendations for in service training for Judges and Prosecutors respectively for Auxiliary staff were prepared. After assessment of the definite text they will be sent to the High Council for Judges and Prosecutors and the Ministry respectively to the Ministry.

The first Train the Trainers seminar on case flow management for the auxiliary personnel was a success.

We are still positive about the enthusiasm, about the cooperation between the BC and MS experts and about the working relationship between the RTA and his counterpart. We have some observations, which we’ll mention below.

We are happy that at the ministry one extra reporter judge was added to the team, next to the RTA counterpart and the BC component leader of most of the components.

In this period three side letters:

- side letter 6: Additional translation and training material for handbooks Component 2 Twinning Workplan

- side letter 7: Annulation of activity 3.12, Content change of activities 3.14, 3.17and 3.21, Addition of MS expert to 3.14, 3.17 and 3.21

- side letter 8: Change of BC Component leader of the components 1,2 and 4

were presented. They are still pending.

Again some issues need more attention in order to be able to keep up this positive assessment. We will examine these issues below.

Conclusion

In general the assessment is positive. Some issues need further attention.

Issues

Problems in the management of the project or in the co-operation between the partners. Any other issues.

BC input

We again assess the cooperation between BC and MS to be good. However, we have to repeat some concerns.

In both our previous reports we mentioned our concern about too many tasks on the shoulders of the RTA’s counterpart. Although measures to meet this problem were taken, improvement failed to materialize. Still too many tasks take to long (for an example we refer to page 31, recuperation of delays, first conference), too many questions are not answered in time and too many reminders have to be issued. Too often meetings are postponed on very short notice because of suddenly upcoming other tasks that apparently have a higher priority in the Ministry. Sometimes the cooperation even is a bit chaotic. Of course this partly comes to the account of other circumstances, like the problems with translations, but we feel that this mainly is the consequence of the many other tasks on the shoulders of the RTA counterpart and his colleagues in the team. This situation not only causes difficulties for the proper execution of the tasks of the RTA and his assistants, but this also threatens to affect the quality of the results in the project. We again recommend to review the tasks of the RTA’s counterpart as to give him the opportunity to devote (most of) his time to the project and to be the key figure, with whom the RTA can communicate all issues and who has the opportunity to coordinate, supervise and control the activities on BC side.

In the previous reports we also mentioned that we sometimes encountered a lack of participation and preparation on the part of the BC experts. Unfortunately this has not changed. Often (key) experts do not show up or attend only half of the meeting. All working groups are finished now, so w will not face this problem any more, at least not in this way. However, the results of the project continue to depend to a large extent on the input of BC experts and trainers. We trust that the BC will give full support to the project in general and to the Train the Trainers seminars and the Roll out in particular, by facilitating optimizing the necessary personnel input. We will repeat our recommendation.

Handbooks: translation and other problems

The translation problems we suffered in the second quarter, continued in the third. The translation company we selected after the fiasco with the Dutch company was good, but – contrary to what was said initially – could not work on more than one handbook simultaneously. So again we had to find another company. Again we found one and again it was a failure. Finally we found a company that could handle two handbooks at one time and that delivered a reasonable result.

In the mean time it appeared that – opposed to what we agreed in the working groups – the handbooks in the hands of the translators were not the final drafts (that would be subject to amending by the last working group meeting only): they were revised again without clear indication of the new passages. So the source of translation considerably changed during translation. Moreover, after the last meeting of one of the working groups some amendments had to be made again, and again it was impossible to trace the changes. Since the software comparing tools failed here too, the Turkish members of our twinning team had to compare two versions – and for some parts even three versions – by hand and eye, page for page, to find out what had to be translated. The alternative, not applying changes any more, was not acceptable: it would undermine the quality served by the amendments.

This is only a very rough picture of all the problems we encountered with finalizing the handbooks. However, at this moment the Turkish version of the handbooks is ready, the English version almost. This last version is certainly not perfect and still has many deficiencies. But, as we reassured ourselves: it doesn’t need to be a piece of poetry. It should be a reasonably understandable tool for the MS experts to carry out their tasks in the Train the Trainers seminars en the Roll out and to communicate with their Turkish counterparts, trainers and trainees when referring to passages in the Turkish version. And that is what they are.

1st intensive seminar on case-flow management for auxiliary personnel

The decision to change the character of the first seminar of the Train the Trainers program turned out to be a very wise one. The BC and MS experts certainly needed the two days we reserved for getting acquainted to each other, to draft the program for the other two seminars and to divide tasks. These two days were very fruitful. The third day – training in didactics for the whole group of trainers – was a success too.

Final conclusion

Our concerns in this report to a certain extent have a critical undertone. They all are related to increasing apprehension about both the feasibility of opening the Courts of Appeal on 1 June 2007 and about the level of priority the BC is giving to the project. We hereafter repeat our key-recommendations. The project is halfway now. We have been assured that it is not yet too late to carry out the required preparations. We think that for the sake of the well-functioning of the Courts of Appeal and of the success of this project it is necessary that these recommendations are given attention to at the highest level.

Summing up of recommendations and conclusions (2A, 2D and 2E)

Recommendations regarding the assumptions (2A)

We reiterate and strongly recommend the Turkish authorities to take all necessary steps mentioned in IQR 1 and 2 under 2A urgently and to give full clarity about the decision-making process and the time schedule within the coming weeks. The fulfilment of these recommendations is crucial for the success of the project and the establishment of the Courts of Appeal in general.

So we strongly recommend the Turkish authorities

- to intensify the information to the judiciary

  - about the establishment of the Courts and the reasons behind this operation,

  - about the goal of the project and the efforts taken to achieve that goal,

- to take the necessary steps without any delay in order

  - to deal with the relevant appointments

  - to appoint Presidents and ‘quartermasters’ (with the qualifications of a possible President of a Court of Appeal) to each future Court of Appeal in order to take care of the preparations

  - to decide upon the number of Courts of  Appeal, their seats and their jurisdiction

  - to take care of the premises, organisation and infrastructure of all Courts of Appeal

  - to draft the necessary Bylaws for the functioning of the courts

  - to provide the necessary funds

  - and to have all the stakeholders ready and informed.

We recommend taking the necessary steps without any delay and to give full clarity about the decision-making process and the time schedule in respect of the Courts of Appeal.

Conclusions (2D and 2E)

Delays

- The publishing of a booklet and the report of recommendations under activity 1.2, 1.3 and 1.7 (First conference of Judges and Prosecutors of the Court of Cassation) have not yet been finalized. This is expected for November.

Other recommendations (2E)

- We recommend to review the tasks of the RTA’s counterpart as to give him the opportunity to devote (most of) his time to the project and to be the key figure, with whom the RTA can communicate all issues and who has the opportunity to coordinate, supervise and control the activities on BC side.

- We repeat our recommendation to intensify the information about the establishment of the Courts and the reasons behind it to the judiciary and to give full support to the project in general by facilitating the necessary personnel input.

General and final conclusion (2E)

In general the assessment is positive again. Some issues (still) need further attention.

We think that for the sake of the well-functioning of the Courts of Appeal and of the success of this project it is necessary that the recommendations in this report are given attention to at the highest level.

Attachments: the activity reports of all activities in the reporting period.

Terug naar Ingelse & Cath

# Footnotes

+ means: fulfilled.

+ means: fulfilled.

According to article 3 of the Workplan month 18, but obviously for the first conference it is month 6 (article 4, under activity 1.7).