## Terug naar Ingelse & Cath

# TWINNING  INTERIM QUARTERLY REPORT number: Five

# EUROPEAN COMMISSION

# TWINNING PROJECTS

# INTERIM QUARTERLY REPORT

# Project Title: Support to the establishment of Courts of Appeal in the Republic of Turkey

# Partners:  Ministry of Justice of the Republic of Turkey and the Netherlands Council for the Judiciary and the Swedish National Courts Administration

Date: April 2007

Section 1: Project data

| Twinning Contract Number | TR 2004/IB/JH-01 |
| --- | --- |
| Project Title: | Support to the establishment of Courts of Appeal in the Republic of Turkey |
| Twinning Partners (MS and BC) | Netherlands Ministry of Justice (administrative authority) in cooperation with the Netherlands Council for the Judiciary (implementing authority) as leading MS and the Swedish National Courts Administration Junior MS. The Ministry of Justice of the Republic of Turkey |
| Report Number: | Five |
| Period covered by the report: | 19 January 2007- 18 April 2007 |
| Duration of the project: | 18 months |
| Rapporteur: | Mr. A.H. van Delden |

Section 2: Content

2A – BACKGROUND

2B – ACHIEVEMENT OF MANDATORY RESULTS

2C – ACTIVITIES IN THE REPORTING PERIOD

2D – TIMING AND DELAYS

2E – ASSESSMENT

2A - BACKGROUND

Policy Developments

- What were the key developments in the relevant policy area in the BC in the reporting period?

Until this moment, still no decision has been taken regarding the number of Courts of Appeal, their location, their territorial jurisdiction or the buildings where they will start functioning. No President of the Courts or ‘quarter masters’ and no Judges, Public Prosecutors or auxiliary staff members have been appointed yet.

It is very unlikely that the courts can be opened on 1 June 2007, the latest possible date according to the Law on the establishment, duties and powers of the ordinary Courts of First Instance and Regional Courts of Appeal. True, as we were told, it is not inconceivable that the courts physically start later than 1 June 2007 without changing the law. In the starting period it will take some time before a case load will have been built up, so that might again give a few months’ grace. However, in that scenario too, there is no time left for delay of further preparatory activities. According to the aforementioned Law the Minister of Justice, the High Council for Judges and Public Prosecutors and other authorities each have their own clear responsibilities, but we cannot see any movement on the essential issues. It is inevitable to put question marks with respect to the continued political support to the timely establishment of the Courts of Appeal.

There are some developments that strongly highlight these question marks: the general elections in the near future, the Courts of first instance (again) and the appointment of members of the Court of Cassation. Below we elaborate on these issues shortly.

The general elections in the near future

In November general elections will be held. Three months before the election the Minister of Justice (together with the Ministers of Transport and Home Affairs ones) will be replaced with a politically independent Minister. According to what we are told this might affect the activities for the establishment of Courts of Appeal.

The Courts of first instance

In our IQR 4 we reported about the court case that the association Yarsav (“Union of Judges and Prosecutors”, established last summer) filed against the Ministry about the selection of some hundreds of candidate judges and public prosecutors. As mentioned in that report the Council of State suspended the selection decision and referred the case to the Constitutional Court. Thereupon the Constitutional Court decided that the selection decision was not unconstitutional and the Council of State lifted the suspension. However, recently we were informed that the Council of State – this time the General Chamber – on the request of Yarsav again suspended the decision. The relevant By-law is supposed to be unconstitutional. Again this means that the recruitment of candidates for the courts of first instance will be blocked. And once again this stresses the concerns of the High Council for Judges and Public Prosecutors about the fact that the appointment of 1000 judges and prosecutors for the Courts of Appeal will take away one third of the best judges and prosecutors from the top of the first instance courts without any supplement at the bottom.

We deem it necessary to mention here that a law is pending in parliament regarding the establishment of a public body for Judges and Prosecutors. This law will outlaw associations of Judges and Prosecutors other than cultural and sport associations, which would 	entail the end of Yarsav. We do not want to comment on this law here, but we mention it to show how the Courts of Appeal are established in a to some extent tense environment.

The appointment of members of the Court of Cassation

During PSC meeting 4 we were informed that the law amending the law on the Court of Cassation, which is essential and condition sine qua non for the establishment of Courts of Appeal, would reduce the number of members of the Court of Cassation from 250 to 150 and that this law would be passed through parliament end of February. However the law is still pending. A few weeks ago the newspapers brought the news, that (the judicial members of) the High Council want(s) to appoint 23 members of the Court of Cassation to bring the number on 250 again, despite the soon expected decrease of this number. This raised differences of opinion between the Ministry and the High Council. According to the most recent information the differences have been settled: the High Council has met again on 15 April 2007 and effectuated the appointments. It is difficult to understand how these appointments are supposed to be consistent with the envisaged start of the Courts of Appeal and the decrease of the number of members of the courts of cassation just two months later.

PSC 5 meeting

All these developments can have a (negative) impact on the establishment of the Courts of Appeal. We would appreciate it if the Ministry and the High Council could update us during the PSC 5 meeting about the most recent developments and preparatory measures.

Project Assumptions

- Which of the original assumptions of the project (Article 2 of the Work plan) have been fulfilled?

- Which of them are likely to be fulfilled soon?

- Have there been any developments, which make some of the assumptions impossible to achieve? (If yes, the project requires reorientation)

The following assumptions are mentioned in article 3 of the Workplan.

|  | Assumptions | Status quo IQR 3 | Status quo IQR 4 | Status quo IQR 5 |
| --- | --- | --- | --- | --- |
| Overall objective | Continued political support for the reform of the judiciary by the Ministries, the Parliament and the Court of Cassation Support and commitment from all stakeholders within the judiciary and in particular the Court of Cassation Availability of financial resources in order to cover all needs of the newly established courts Support and commitment of High Council for Judges and prosecutors. Where the appointment and establishment delays, the Republic of Turkey shall train all the prospective judges, prosecutors and auxiliary personnel | See below | See below | See below |
| Project purpose | Continued political support by Ministries, the Parliament and the Court of Cassation for the reform of the judiciary and the quick establishment and effective functioning of the Courts of Appeal Judges, prosecutors and auxiliary personnel for the Courts of Appeal appointed on time by the High Council for Judges and Prosecutors and available to participate in the activities of the project and in particular in the training | See below | See below | See below |
| Mandatory results | The High Council for Judges and Prosecutors selects and appoints judges and prosecutors and auxiliary personnel timely Involvement and support of the Justice Academy Continued political support by the Ministries, the Parliament and the Judiciary Continued support of the Stakeholders, including the judges and prosecutors of the Court of Cassation Active involvement of judges and prosecutors in training Sufficient finances and human resources allocated by the Turkish government | See below | See below | See below |
| Kick off meeting | Turkish authorities support the informing of the public at large about the reform of the judicial system | + | See Act. 3.28, visit to the regions | See Act. 3.28, visit to the regions |
| Component 1 | Commitment of the judges and prosecutors of the Court of Cassation and their availability to attend the conferences | + | Second conference to be held in the last quarter | Second conference to be held in the last quarter |
| Component 3 | Judges and prosecutors appointed on time. The Ministry of Justice will take care of the extra training activities. Support of the TtT approach both by the ministry and the stakeholders Criteria for trainers (qualifications, experience in training etc) are elaborated and ready on time | See below | See below | See below + + |
| Component 3 Block B | Trainers timely identified Future trainers committed to be trained and to later train their colleagues in CoA and co-operate with the Justice Academy High Council for Judges and Prosecutors appoints the judges, prosecutors and auxiliary staff for the Courts of Appeal before the start of the training. High Council for Judges and Prosecutors releases judges and prosecutors and auxiliary personnel will be released for training Judges, prosecutors and auxiliary personnel will absorb the training Support and commitment of High Council for Judges and prosecutors | See below | See below | + + See below + + + |
| Component 4 | Influential officials being selected and available for the visit | + | + | + |
| Component 4 activity 4.1 | Officials being committed to technically take profit of the visit to better understand the Appeal System in NL and FR and use their impressions in adjusting the introduced system in Turkey | + | + | + |
| Round up of the project | Participation of stakeholders to the conference Participation of media to the press conference | See below | See below |  |

Comments

Our comments under ‘Policy Developments’ of course are relevant here too. They affect all assumptions 1-13. We reiterate the question marks with respect to the continued political support to the timely establishment of the Courts of Appeal. We would be very much obliged if the Ministry and the High Council could update us during the PSC 5 meeting about the most recent developments and preparatory measures.

2B - ACHIEVEMENT OF MANDATORY RESULTS

- List all the benchmarks which were achieved in the reporting period within each of the components and indicate which of the Intermediate Results and Mandatory Results are completed or close to completion.

| Benchmarks | Ready by month | Status quo IQR 3 | Status quo IQR 4 | Status quo IQR 5 |
| --- | --- | --- | --- | --- |
| COMPONENT ONE: Conferences for Judges and Prosecutors of the Court of Cassation |  |  |  |  |
| Component Benchmarks achieved: |  |  |  |  |
| Agendas and material for first conference prepared |  | + | + | + |
| One conference carried out |  | Will be finished in October | See 2 D under ‘recuperation of delays’ | + |
| Activity Benchmarks achieved: |  |  |  |  |
| 1.1 Agenda of the conference finalized | 2 | + | + |  |
| 1.2 Conference carried out and documentation thereof disseminated | 3 | Will be finished in October | + See 2 D under ‘recuperation of delays’ | + |
| 1.3 Publication and dissemination of the speeches and a summary of the discussion at the first conference | 6 | Will be finished in October | See 2 D under ‘recuperation of delays’ | + |
| 1.7 Recommendations of the first conference gathered and forwarded to the relevant persons within the Ministry of Justice | 6 | + | + See 2 D under ‘recuperation of delays’ | + |
| COMPONENT TWO: Preparation of handbooks for the Courts of Appeal |  |  |  | + |
| Component Benchmarks achieved: |  |  |  | + |
| Activity Benchmarks achieved: |  |  |  |  |
| 2.1 Assessment report with findings and recommendations regarding Civil Procedure handbook content ready | 2 | + | + | + |
| 2.2 Agreed table of content for Civil Procedure handbook and plan of action with tasks’ division prepared | 3 | + | + | + |
| 2.3 A draft handbook ready and submitted for comments to the BC stakeholders | 5 | + | + | + |
| 2.4 First complete version of handbook ready, 3000 copies of handbook printed and disseminated | 9, 13 | Third meeting of the working group on the preparation of civil handbook focused on review of the complete version of the handbook, some amendments to be drafted by MS experts were suggested. These have been received in October. After acceptation by BC experts and translation, the first complete version of the handbook will be ready by project month 11. | Handbook ready. Printing ready soon. | + |
| 2.5 Assessment report with findings and recommendations regarding Criminal Procedure handbook content ready | 2 | + | + | + |
| 2.6 Agreed table of content for Criminal Procedure handbook and plan of action with tasks’ division ready | 3 | + | + | + |
| 2.7 A draft handbook ready and submitted for comments to the BC stakeholders | 5 |  | + | + |
| 2.8 First complete version of handbook ready, 6000 copies of handbook printed and disseminated | 9, 12 | Third meeting of the working group on the preparation of criminal handbook was convened to review the final version of the handbook. Some amendments were recommended and applied on the book in early October. As the amendments made were not indicated, twinning team is working to identify amendments in the latest Turkish version so that the English version is harmonized accordingly. The first complete version of the handbook is expected to be ready by the end of October. | It took quite a lot time to identify, fix and get translated the amendments of the Criminal Handbook. Completed by the end of December. Printing ready soon. | + |
| 2.9 Joint methodology and content for the handbooks agreed on by the different working groups | 3 | + | + | + |
| 2.10 Assessment report with findings and recommendations regarding Auxiliary personnel handbook content ready | 3 | + | + | + |
| 2.11 Agreed table of content for Auxiliary personnel handbook and plan of action with tasks’ division ready | 4 | + | + | + |
| 2.12 A draft handbook ready and submitted for comments to the BC stakeholders | 6 | + | + | + |
| 2.13 First complete version of handbook ready, 150 copies of handbook printed, agenda of evaluation workshop ready | 8 | + The missing parts of this handbook in the second reporting period were completed in the third reporting period. Newly added parts are also translated and integrated to the former translation of the handbook. The efforts of the twinning team to harmonize both translations and increase the quality of the English translation of the handbook is still going on | Handbook ready. Printing ready soon. | + |
| 2.14 Evaluation report on handbook ready, amendments of handbook incorporated, 2000 copies of handbook ready for dissemination | 11 | Evaluation meeting was carried out in October. Participants had all reviewed the book at length and thus fruitful discussions took place in the evaluation meeting. The report of this meeting and incorporation of amendments to the handbook are expected to be done in the shortest possible time, assignments of these duties are done. | + | + |
| COMPONENT THREE: Training of Judges, Prosecutors and Auxiliary personnel of the Courts of Appeal |  |  |  | + |
| Component Benchmarks achieved: |  |  |  | + |
| TNA for judges and prosecutors performed Course on Civil Procedure for Judges developed Course on Criminal Procedure for Judges and Prosecutors developed Course on Case-flow management for Auxiliary personnel developed |  | + + + + + | + + + + | + + + + |
| Activity Benchmarks achieved: Block A |  |  |  | + |
| Training needs analysis and development of training courses |  | + | + | + |
| 3.1 TNA for judges and prosecutors executed, experts’ report with recommendations on topics ready | 4 | + | + | + |
| 3.2 Minutes of meeting, record of course content and methodology, record of background material, ready | 5 | + | + | + |
| 3.3 First draft of the course, including plan of content, methodology and record of gathered information ready | 6 | + | + | + |
| 3.4 Course (final version) ready | 8 | + In the third reporting period the remaining tasks of 3.4 are completed. | + | + |
| 3.5 Minutes of the meeting, record of course content and methodology, record of background material ready | 5 | + | + | + |
| 3.6 First draft of the course, including plan of content, methodology and record of gathered information, ready | 6 | + | + | + |
| 3.7 Course (final version), ready | 8 | Some of the background material still has to be translated | + | + |
| 3.8 An in-service training provision for judges and prosecutors | 11 | + Recommendations ready in draft. Yet to be approved by BC experts. |  | + |
| 3.9 TNA for auxiliary personnel executed, experts’ report with recommendations on topics ready | 5 | + | + | + |
| 3.10 Minutes of the meeting, record of course content and methodology, record of background material, ready | 6 | + | + | + |
| 3.11 First draft of the course curriculum, including plan of content, methodology and record of gathered information, ready | 7 | + Remaining translation task is completed in the third reporting period. | + | + |
| 3.12 Course (final version), ready | 8 | + | + | + |
| 3.13 An in-service training provision for auxiliary personnel ready | 11 | + Recommendations ready in draft. Yet to be approved by BC experts. | + | + |
| Block B: |  |  |  | + |
| Train the Trainers |  |  |  |  |
| 3.14 Curriculum for TtT developed according to course curriculum, training in didactics conducted | 11 | + | + | + |
| 3.15 15 future trainers trained according to course, notes from the seminar on discussed cases and material typed out, evaluation by Turkish participants compiled | 12 |  | + | + |
| 3.17 Curriculum for TtT developed according to course curriculum, training in didactics conducted | 11 |  | + | + |
| 3.20 A 5-day Study visit for 15 future trainers of judges and prosecutors to Netherlands completed, evaluated and reported by month 12; basis for future contacts within courts network established | 12 |  | + | + |
| 3.21 Curriculum for TtT developed according to course curriculum, training in didactics conducted | 9 |  | + | + |
| 3.22 25 future trainers trained according to course curriculum, notes from the seminar on discussed cases and material typed out, evaluation by Turkish participants compiled, by project month 11 | 11 |  | + | + |
| 3.23 25 future trainers trained according to course curriculum, notes from the seminar on discussed cases and material typed out, evaluation by Turkish participants compiled, by project month 12 | 12 | + | + | + |
| 3.24 A 5-day Study Visit for 15 future trainers of auxiliary personnel to Sweden completed, evaluated and reported by month 11 | 11 |  | + | + |
| 3.28 Information on project Disseminated by month 12. A 5-day visit of RTA and counterpart to three regions to gather information from local judges, public prosecutors and auxiliary staff completed by month 12. Report with expectations and recommendations ready by month 13 | 13 |  | + | + |
| Block C: |  |  |  |  |
| Training programme |  |  |  |  |
| Not yet completed |  |  |  | 21 Roll out seminars (civil, criminal and auxiliary staff) have been carried out |
| COMPONENT FOUR: Acquainting Turkish officials from the Ministry of Justice and the Justice Academy with the Appeal System in EU MS |  | + | + | + |
| Component Benchmarks achieved: |  |  |  |  |
| Participants of study visit acquainted with judicial systems in NL and France |  | + | + | + |
| Activity Benchmarks achieved: |  |  |  |  |
| 4.1 A 10-day Study Visit for 10 Turkish officials to the NL and FR completed, evaluated and reported | 3 | + | + | + |
| 4.1 Basis for courts network for future contacts and collaboration established |  | + | + | + |

2C. ACTIVITIES IN THE REPORTING PERIOD

- Component by component, list all the activities which have taken place in the reporting period in the order in which they appear in the Work plan and providing their reference numbers.

- For each activity specify the following details:

(1) Reference number and title of Activity (as in Art 3 of the Work plan);

(2) Names of MS experts who delivered it;

(3) Number of experts from the BC who participated and their departments of origin

(4) Duration of the activity

We have attached the activity reports of all activities in the reporting period.

Component one: Conferences for Judges and Prosecutors of the Court of Cassation

Activity 1.4: Preparation of the agenda of the second conference for judges and prosecutors of the Court of Cassation

Duration: One day (13 February 2007)

MS experts

- Mr. Huydecoper, Advocate General  Netherlands Supreme Court

- Mr. Bjornberg, Chamber President of the Court of Appeal for Western Sweden

- Mr. Ingelse, Vice-President Court of Appeal, Amsterdam and RTA

BC experts

  - Mr. Haluk Beşer, Court of Cassation Deputy Secretary General

  - Mr. Ibrahim Sahbaz, Court of Cassation Public Prosecutor

  - Mr. Osman Yurdakul, Court of Cassation Deputy Secretary General

  - Mr. Celalettin Dönmez, RTA counterpart, BC activity co-ordinator

Component three: Training of Judges, Prosecutors and Auxiliary personnel of the Courts of Appeal

Activity 3.16: Third intensive seminar on civil procedure for future trainers of judges

Duration: Three days (24-26 January 2007)

MS experts

- Mr. G.J. Visser Vice-president and justice Court of Appeal Amsterdam

- Mr. W.F. Korthals-Altes, Justice Court of Appeal Arnhem

- Ms. Marianne Lejman, Judge of Appeal, Court of Appeal for Skåne and Blekinge

BC experts

- Mr. Ass Prof Muhammed Ozekes (Eylul University, Izmir)

- Ms. Mine Kaya (Court of Cassation, Reporter Judge)

- Mr. Salih Ozaykut (Court of Cassation, Reporter Judge)

- Mr. Osman Caliskan (General Directorate of Legislation, Reporter Judge)

List of trainers

- Mr. Adem Aslan (Ankara, Judge)

- Mr. Adem Albayrak (Ankara, Judge)

- Ms. Inci Babacan Bickin (Court of Cassation, Reporter Judge)

- Mr. Gurkan Ahmet Genckaya (Court of Cassation, Reporter Judge)

- Ms. Candas Ilgun (Ankara, Judge)

- Mr. Ilker Kocyigit (Ankara, Judge)

- Mr. Ibrahim Catalkaya (Ankara, Judge)

- Mr. Esat Ozdem (Court of Cassation, Reporter Judge)

- Mr. Haydar Aydin (İstanbul, Judge)

- Mr. Gultekin Dinc (Court of Cassation, Reporter Judge)

- Ms. Filiz Budak (Court of Cassation, Reporter Judge)

- Mr. Yilmaz Tosun (Court of Cassation, Judge)

- Ms. Fatma (Akyuz) Ozturk (Kucukcekmece, Judge)

- Ms. Dondu Deniz Biltekin (Court of Cassation, Judge)

- Ms. Fatma Turhan (Bursa, Judge)

Activity 3.18: Second intensive seminar on Criminal procedure for future trainers of judges and prosecutors

Duration: Three days (17-19 January 2007)

## MS experts:

- Mr. Piet Hein A.J. Cremers, Chief Public Prosecutor, Court of Appeal `s-Hertogenbosch (NL)

- Mr. Gerritjan van Oven, Justice, Court of Appeal, The Hague

- Ms. Monique Hugo, Deputy General Prosecutor at the Court of Appeal of Lyon

- Mr. Håkan  Nyberg, Chief Judge, Varberg District Court

BC experts:

- Mr. Prof Dr Bahri Özturk---Istanbul Kultur University; Dokuz Eylul University

- Mr. Dr. Fazli Dogan, General Directorate of International Law and Foreign affairs, head of chamber

- Mr. Hasan Tahsin Gokce, Court of Cassation, reporter judge

- Mr. Dr Teoman Gokce, Court of Cassation, reporter Judge

List of Trainers:

1.    Mr. Beytullah Metin (Court of Cassation, Reporter Judge)

2.    Mr. Necati Meran (Court of Cassation, Reporter Judge)

3.    Mr. Mesut Budak (Court of Cassation, Reporter Judge)

4.    Mr. Hazma Yalcinkaya (Kirsehir Courthouse, Judge)

5.    Mr. Ali Sancar (Gaziantep, Head of Criminal Court)

6.    Mr. Ismail Ademoglu (Kirsehir, Head of Criminal Court)

7.    Mr. Muammer Karatas (Karsiyaka Courthouse, Judge)

8.    Mr. Husamettin Ugur (Court of Cassation, Reporter Judge)

9.    Mr. Rasim Kont (Ankara, Head of Criminal Court)

10.  Mr. Battal Ozer (Adana, Head of Criminal Court)

11.   Mr. Mehmet Resat Koparan (Kayseri, Judge)

12.   Mr. Berkun Koksal (Sinop, Head of Criminal Court)

13.   Mr. Muzaffer Karadag (Kutahya, Head of Criminal Court)

14.   Ms. Ozlem Aksoy (Bafra, Judge)

15.   Mr. Kadri Atalay (Izmir, Judge)

16.   Mr. Mustafa Albayrak (Court of Cassation, Reporter Judge)

17.   Mr. Yahya Akcadirci (Ceyhan, Chief Public Prosecutor)

18.   Mr. Cemil Kuyu (Mersin, Chief Public Prosecutor)

19.   Mr. Bilal Gunduz (Ankara, Public Prosecutor)

20.   Mr. Ferhat Kapici (Yozgat, Chief Public Prosecutor)

21.   Mr. Ilhan Cihaner (Alasehir, Chief Public Prosecutor)

22.   Mr. Yusuf Ulu (Kartal, Chief Public Prosecutor)

23.   Mr. Nuri Yigit (Tekirdag, Chief Public Prosecutor)

24.   Mr. Huseyin Guler (Antalya, Public Prosecutor)

25.   Mr. Kadir Yilmaz (Erzurum, Chief Public Prosecutor)

Activity 3.19 Third intensive seminar on Criminal procedure for future trainers of judges and prosecutors

Duration: Three days (14 -16 February 2007)

MS experts

- Mr. Piet Hein A.J. Cremers, Chief Public Prosecutor, Court of Appeal 
`s-Hertogenbosch (NL)

- Mr. Gerritjan van Oven, Justice, Court of Appeal, The Hague

- Ms. Monique Hugo, Deputy General Prosecutor at the Court of Appeal of Lyon

- Mr Håkan  Nyberg, Chief Judge, Varberg District Court

BC experts

- Mr. Prof Dr Bahri Özturk---Istanbul Kultur University; Dokuz Eylul University

- Mr. Dr. Fazli Dogan, General Directorate of International Law and Foreign affairs, head of chamber

- Mr. Hasan Tahsin Gokce, Court of Cassation, reporter judge

- Mr. Dr. Teoman Gokce, Court of Cassation, reporter Judge

List of Trainers

1.    Mr. Beytullah Metin (Court of Cassation, Reporter Judge)

2.    Mr. Necati Meran (Court of Cassation, Reporter Judge)

3.    Mr. Mesut Budak (Court of Cassation, Reporter Judge)

4.    Mr. Hazma Yalcinkaya (Kirsehir Courthouse, Judge)

5.    Mr. Ali Sancar (Gaziantep, Head of Criminal Court)

6.    Mr. Ismail Ademoglu (Kirsehir, Head of Criminal Court)

7.    Mr. Muammer Karatas (Karsiyaka Courthouse, Judge)

8.    Mr. Husamettin Ugur (Court of Cassation, Reporter Judge)

9.    Mr. Rasim Kont (Ankara, Head of Criminal Court)

10.  Mr. Battal Ozer (Adana, Head of Criminal Court)

11.  Mr. Mehmet Resat Koparan (Kayseri, Judge)

12.  Mr. Berkun Koksal (Sinop, Head of Criminal Court)

13.  Mr. Muzaffer Karadag (Kutahya, Head of Criminal Court)

14.  Ms. Ozlem Aksoy (Bafra, Judge)

15.  Mr. Kadri Atalay (Izmir, Judge)

16.  Mr. Mustafa Albayrak (Court of Cassation, Reporter Judge)

17.  Mr. Yahya Akcadirci (Ceyhan, Chief Public Prosecutor)

18.  Mr. Cemil Kuyu (Mersin, Chief Public Prosecutor)

19.  Mr. Bilal Gunduz (Ankara, Public Prosecutor)

20.  Mr. Ferhat Kapici (Yozgat, Chief Public Prosecutor)

21.  Mr. Ilhan Cihaner (Alasehir, Chief Public Prosecutor)

22.  Mr. Yusuf Ulu (Kartal, Chief Public Prosecutor)

23.  Mr. Nuri Yigit (Tekirdag, Chief Public Prosecutor)

24.  Mr. Huseyin Guler (Antalya, Public Prosecutor)

25.  Mr. Kadir Yilmaz (Erzurum, Chief Public Prosecutor)

Activity 3.25 Training seminar for judges dealing with civil cases

Duration: Two days in Ankara (26-27 February 2007)

MS experts

- Mr. G.J.Visser, Vice-president and Justice Court of Appeal Amsterdam

- Ms. Marianne Lejman, Judge of Appeal, Court of Appeal for Skåne and Blekinge

BC trainers

  - Mr. Adem Albayrak, Ankara Judge

  - Mr. İlker Koçyiğit, Ankara Judge

  - Mr. İbrahim Çatalkaya, Ankara Judge

  - Ms. Deniz Biltekin, Reporter Judge at the Court of Cassation

Number of trainees: 45

Activity 3.25 Training seminar for judges dealing with civil cases

Duration: Two days in Istanbul (1-2 March 2007)

MS experts

- Mr. G.J.Visser, Vice-president and Justice Court of Appeal Amsterdam

- Ms. Marianne Lejman, Judge of Appeal, Court of Appeal for Skåne and Blekinge

BC trainers

- Ms. Fatma Akyüz, Istanbul Küçükçekmece Judge

- Mr. Haydar Aydın, Istanbul Judge

- Ms. Fatma Turhan, Bursa Judge

- Mr. Yılmaz Tosun, Reporter Judge at the Court of Cassation

Number of trainees: 46

Activity 3.25 Training seminar for judges dealing with civil cases

Duration: Two days in Istanbul (26-27 March 2007)

MS experts

- Ms. A.J.M.E. Arpeau, Justice Court of Appeal The Hague, Netherlands

- Ms. Marianne Lejman, Judge of Appeal, Court of Appeal for Skåne and Blekinge, Sweden

BC trainers

- Ms. Fatma Akyüz, Judge at İstanbul Küçükçekmece

- Ms. Deniz Biltekin, Reporter Judge at Court of Cassation

- Mr. Esat Özdem, Reporter Judge at Court of Cassation

- Mr. Adem Albayrak, Ankara Judge

Number of trainees: 46

Activity 3.25 Training seminar for judges dealing with civil cases

Duration: Two days in Ankara (29-30 March 2007)

MS experts

- Ms. A.J.M.E. Arpeau, Justice Court of Appeal The Hague, Netherlands

- Ms. Marianne Lejman, Judge of Appeal, Court of Appeal for Skåne and Blekinge, Sweden

BC trainers

- Mr. Gültekin DİNÇ, Reporter Judge at the Court of Cassation

- Mr. Deniz Biltekin, Reporter Judge at the Court of Cassation

- Mr. Esat Özdem, Reporter Judge at the Court of Cassation

- Ms. Filiz Budak, Reporter Judge at the Court of Cassation

Number of trainees: 43

Activity 3.25 Training seminar for judges dealing with civil cases

Duration: Two days in Gaziantep (2-3 April 2007)

MS experts

- Mr. G.J.Visser, Vice-president and Justice Court of Appeal Amsterdam

- Mr. K. Björnberg, Chamber President of the Court of Appeal for Western Sweden

BC trainers

- Mr. Adem ALBAYRAK, Ankara Judge

- Mr. Ercan TURAN, Reporter Judge Court of Cassation

- Ms. Fatma TURHAN, Bursa Judge

- Ms. Filiz BUDAK, Reporter Judge Court of Cassation

Number of trainees: 42

Activity 3.25 Training seminar for judges dealing with civil cases

Duration: Two days in Ankara (5-6 April 2007)

MS experts

- Mr. G.J.Visser, Vice-president and Justice Court of Appeal Amsterdam

- Mr. K. Björnberg, Chamber President of the Court of Appeal for Western Sweden

BC trainers

- Mr. Haydar Aydin, Istanbul Judge

- Mr. Ercan Turan, Reporter Judge Court of Cassation

- Mr. Yılmaz Tosun, Reporter Judge Court of Cassation

- Mr. Gültekin Dinç, Reporter Judge Court of Cassation

Number of trainees: 42

Activity 3.26 Training seminar for judges dealing with criminal cases and prosecutors

Duration: Two days in Ankara (19-20 March 2007)

MS experts

- Ms. M.M.A. Hugo, Deputy General Prosecutor at the Court of of Appeal of Lyon, France

- Mr. K. Björnberg, Chamber President of the Court of Appeal for Western Sweden

BC trainers

Mr. Dr Teoman Gökçe, Reporter Judge at the Court of Cassation

Mr. Mehmet Reşat Koparan, Kayseri Judge

Mr. Kadir Yılmaz, Şanlıurfa Chief Public Prosecutor

Mr. Yahya Akçadırcı, Van Chief Public Prosecutor

Mr. Berkün Köksal, President of Sinop Heavy Criminal Court

Number of trainees: 49

Activity 3.26 Training seminar for judges dealing with criminal cases and prosecutors

Duration: Two days in Istanbul (22-23 March 2007)

MS experts

- Ms. M.M.A. Hugo, Deputy General Prosecutor at the Court of of Appeal of Lyon, France

- Mr. K. Björnberg, Chamber President of the Court of Appeal for Western Sweden

BC trainers

Mr. Dr. Fazlı Doğan, Head of Chamber at the General Directorate of International Law and Foreign Affairs

Mr. Nuri Yiğit, Tekirdağ , Chief Public Prosecutor

Mr. Beytullah Metin, Reporter Judge at the Court of Cassation

Mr. Kadri Atalay, Judiciary Inspector

Ms. Özlem Aksoy, Bafra Judge

Number of trainees: 45

Activity 3.26 Training seminar for judges dealing with criminal cases and prosecutors

Duration: Two days in Ankara (26-27 March 2007)

MS experts

- Mr. B. Ahnborg, Judge of Appeal, Svea Court of Appeal, Sweden

- Mr. G.J.W. van Oven, Justice Court of Appeal in The Hague, Netherlands

BC trainers

- Mr. Bahri Öztürk (Oturum Başkanı), Professor at the Kültür University, Faculty of Law

- Mr. Necati Meran, Reporter Judge at the Court of Cassation

- Mr. Bilal Gündüz, Ankara Public Prosecutor

- Mr. Ali Sancar, President of the Gaziantep Heavy Penal Court

- Mr. Cemil Kuyu, Mersin Chief Public Prosecutor

Number of trainees: 48

Activity 3.26 Training seminar for judges dealing with criminal cases and prosecutors

Duration: Two days in Erzurum (29-30 March 2007)

MS experts

- Mr. B. Ahnborg, Judge of Appeal, Svea Court of Appeal, Sweden

- Mr. G.J.W. van Oven, Justice Court of Appeal in The Hague, Netherlands

BC trainers

Mr. Dr Teoman Gökçe, Reporter Judge at the Court of Cassation

Mr. Mehmet Reşat Koparan, Kayseri Judge

Mr. Kadir Yılmaz, Şanlıurfa Chief Public Prosecutor

Mr. Yahya Akçadırcı, Van Chief Public Prosecutor

Mr. Berkün Köksal, President of Sinop Heavy Penal Court

Number of trainees: 48

Activity 3.26 Training seminar for judges dealing with criminal cases and prosecutors

Duration: Two days in Ankara (2-3 April 2007)

MS experts

- Mr. A.R.O. Mooy, Justice Court of Appeal Den Bosch, The Netherlands

- Mr. H. Nyberg, Chief Judge, Varberg District Court, Sweden

BC trainers

- Mr. Prof. Dr. Bahri Öztürk (Oturum Başkanı), Professor at the Kültür University, Faculty of Law

- Mr. Battal Özer, President of Adana Heavy Penal Court

- Mr. İsmail Ademoğlu, President of Kırşehir Heavy Penal Court

- Mr. Ferhat Kapıcı, Sakarya Chief Public Prosecutor

- Mr. Mustafa Albayrak, Reporter Judge at the Court of Cassation

Number of trainees: 48

Activity 3.26 Training seminar for judges dealing with criminal cases and prosecutors

Duration: Two days in Ankara (5-6 April 2007)

MS experts

- Mr. A.R.O. Mooy, Justice Court of Appeal Den Bosch, The Netherlands

- Mr. H. Nyberg, Chief Judge, Varberg District Court, Sweden

BC trainers

- Mr. Prof. Dr. Bahri Öztürk (Oturum Başkanı), Professor at the Kültür University, Faculty of Law

- Mr. Battal Özer, President of Adana Heavy Penal Court

- Mr. İsmail Ademoğlu, President of Kırşehir Heavy Penal Court

- Mr. Ferhat Kapıcı, Sakarya Chief Public Prosecutor

- Mr. Mustafa Albayrak, Reporter Judge at the Court of Cassation

Number of trainees: 48

Activity 3.26 Training seminar for judges dealing with criminal cases and prosecutors

Duration: Two days in Izmir (16-17 April 2007)

MS experts

- Mr. Mr. Nico  Tuijn, justice, Court of Appeal ‘s-Hertogenbosch, Netherlands

- Mr. B. Ahnborg, Judge of Appeal, Svea Court of Appeal, Sweden

BC trainers

- Mr. Bahri Öztürk (Oturum Başkanı), Professor at the Kültür University, Faculty of Law

- Mr. Necati Meran, Reporter Judge at the Court of Cassation

- Mr. Bilal Gündüz, Ankara Public Prosecutor

- Mr. Ali Sancar, President of the Gaziantep Heavy Penal Court

- Mr. Cemil Kuyu, Mersin Chief Public Prosecutor

Number of Trainees: 44

Activity 3.27 Training seminar for Auxiliary personnel

Duration: Two days in Ankara (29-30 January 2007)

MS experts

- Ms. Nga Yau Wong, Legal clerk, Court of Appeal of Amsterdam

- Ms. Helena Jonrup, Court Secretary, Court of Appeal for Western Sweden

BC trainers

- Ms. Birsen Samsun, Ankara Head of Clerks

- Mr. Enver Özdemir, Sivrihisar Head of Clerks

- Mr. Naci Güccan, Eyüp Head of Clerks

- Mr. Özgüven Altınok, Nevşehir Head of Clerks

- Mr. Ulvi Karaşahin, Reporter Judge at the Ministry of Justice

Number of trainees: 100

Activity 3.27 Training seminar for Auxiliary personnel

Duration: Two days in Gaziantep (1 -2 February 2007)

MS experts

- Ms. Nga Yau Wong, Legal clerk, Court of Appeal of Amsterdam

- Ms. Helena Jonrup, Court Secretary, Court of Appeal for Western Sweden

BC trainers

- Ms. Birsen Samsun, Ankara Head of Clerks

- Mr. Hikmet Özbay, Malatya Head of Clerks

- Mr. Veli Poyraz, K.Maraş Head of Clerks

- Mr. Fettah Koç, K.Maraş Registry Clerk

- Mr. Mustafa Yabanoğlu ,G.Antep Deputy Chief P. Prosecutor

Number of trainees: 100

Activity 3.27 Training seminar for Auxiliary personnel

Duration: Two days in Samsun (5 -6 February 2007)

MS experts

  - Ms. M. Vriend, Legal clerk (aux. staff), Court of Appeal, Arnhem, NL

- Mr. A. Eka, Senior Judge and Director of  the Swedish Commission on Constitutional Reform

BC trainers

Mr. Alaattin Güdek, Eyüp Registry Clerk

Mr. Orhan Kırman, Ankara Head of Clerks

Mr. Aydın Kapan, Zile Head of Clerks

Mr. Osman Şahbaz, Ankara Head of Clerks

Mr. Vedat Soğukpınar, Samsun P. Prosecutor

Number of trainees: 100

Activity 3.27 Training seminar for Auxiliary personnel

Duration: Two days in Istanbul (8 -9 February 2007)

MS experts

  - Ms. M. Vriend, Legal clerk (aux. staff), Court of Appeal, Arnhem, NL

- Mr. A. Eka, Senior Judge and Director of  the Swedish Commission on Constitutional Reform

BC trainers

Mr. Murat Tanrıöver, Sakarya Registry Clerk

Mr. Yasin Akkaya, Eskişehir Head of Clerks

Mr. Naci Güccan, Eyüp Head of Clerks

Mr. Osman Şahbaz, Ankara Head of Clerks

Mr. İsmail Onaran, İstanbul P. Prosecutor

Number of trainees: 100

Activity 3.27 Training seminar for auxiliary personnel

Duration: Two days in Izmir (8-9 March 2007)

  - MS experts

  - Ms. M. Vriend, Legal clerk (aux. staff), Court of Appeal, Arnhem, NL

  - Mr. K. Björnberg, Chamber President of the Court of Appeal for Western Sweden

  - BC trainers

  - Mr. Selman Atmaca, Denizli Head of Clerks

  - Mr. Hasan Yurtseven, Honaz Head of Clerks

  - Mr. Himmet Yildirim, Denizli Head of Clerks

  - Mr. Ahmet Guzel, Afyon Registry Clerk

  - Mr. Emin Atik, Izmir Deputy Chief Public Prosecutor

Number of trainees: 100

Activity 3.27 Training seminar for auxiliary personnel

Duration: Two days in Istanbul (19-20 March 2007)

MS experts

- Ms. A.M. ten Bosch-Gerritsen, Academic counsel (aux. staff) Court of Appeal Amsterdam, the Netherlands

- Mr. L.T.R. Dahlstedt, Chief Judge, Norrköping District Court, Sweden

BC trainers

Mr. Murat Tanrıöver, Sakarya Registry Clerk

Mr. Yasin Akkaya, Eskişehir Head of Clerks

Mr. Seracettin Zerey, İstanbul Head of Clerks

Mr. Mehmet Demiralay, Isparta Registry Clerk

Mr. Faysal Baydilli, İstanbul Registry Clerk

Number of trainees: 100

Activity 3.27 Training seminar for auxiliary personnel

Duration: Two days in Ankara (22-23 March 2007)

MS experts

- Ms. A.M. ten Bosch-Gerritsen, Academic counsel (aux. staff) Court of Appeal Amsterdam, the Netherlands

- Mr. L.T.R. Dahlstedt, Chief Judge, Norrköping District Court, Sweden

BC trainers

Mr. Selman Atmaca, Denizli Head of Clerks

Mr. Enver Özdemir, Sivrihisar Head of Clerks

Mr. Himmet Yıldırım, Denizli Head of Clerks

Mr. Osman Şahbaz, Ankara Head of Clerks

Mr. Ulvi Karaşahin, MoJ Reporter Judge

Number of trainees: 100

Activity 3.27 Training seminar for Auxiliary personnel

Duration: Two days in Ankara (16 and17 April 2007)

MS experts

- Ms. Nga Yau Wong, Legal clerk, Court of Appeal of Amsterdam

- Mr. L.T.R. Dahlstedt, Chief Judge, Norrköping District Court, Sweden

BC trainers

- Ms. Birsen Samsun, Ankara Head of Clerks

- Mr. Orhan Kırman, Ankara Head of Clerks

- Mr. Naci Güccan, Eyüp Head of Clerks

- Mr. Özgüven Altınok, Nevşehir Head of Clerks

- Mr. Ulvi Karaşahin, Reporter Judge at the Ministry of Justice

Number of Trainees: 100

2D. TIMING AND DELAYS

Adherence to time schedule

Reproduce the Schedule from Article 4 of the Work plan and indicate with a cross in the relevant box all the activities which have taken place from inception of the project until the end of the reporting period.  In this way the reader will see a clear picture of the delays.

Single out those activities which are delayed by more than three months.

|  | Activity planned |
| --- | --- |
| X | Activity performed |
|  | Activity delayed by more than 3 months |

| Project Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Inception of the project |
| Kick-off meeting of the project | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 1 Conferences for judges and Prosecutors of the Court Of Cassation |
| Activity 1.1 Preparation of the agenda for the first conference | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.2 First Conference for judges and prosecutors of the CofC |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity1.3 Publication and dissemination of the first conference |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |
| Activity 1.4 Preparation of the agenda for the Second conference |  |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |  |  |
| Activity 1.5 Second conference for judges and prosecutors of the CofC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.6 Publication after second conference |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.7 Gathering recommendation of the conferences |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |
| Component Result |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | C1 R |

| Project month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Component 2 Preparation of Handbooks for The Courts of Appeal |
| Activity 2.1 Gathering of information and background material concerning civil procedure | X |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.2 First meeting of the WG on Civil Procedure Handbook for Judges in CoA |  | X |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.3 Second meeting of the WG on Civil Procedure Handbook for Judges in CoA |  | X |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.4 Third meeting of the WG on Civil Procedure Handbook for Judges in CoA |  |  |  |  | Postponed |  |  |  | x |  |  |  |  |
| Activity 2.5 Gathering of information and background material concerning criminal procedure | X |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.6 First meeting of the WG on Criminal Procedure Handbook for judges and prosecutors |  | X |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.7 Second meeting of the WG on Criminal Procedure Handbook for judges and prosecutors |  | X |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.8 Third meeting of the WG on Criminal Procedure Handbook for judges and prosecutors |  |  |  |  | Postponed |  |  | X |  |  |  |  |  |
| Activity 2.9 Joint meeting of the Working Groups on Civil and Criminal Procedures |  | X |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.10 Gathering of information on case-flow management and work processes in Turkish courts | X |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.11 First meeting WG on handbook for auxiliary personnel |  | X |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.12 Second meeting WG on handbook for auxiliary personnel |  |  |  | X |  |  |  |  |  |  |  |  |  |
| Activity 2.13 Third meeting WG on handbook for auxiliary personnel |  |  |  |  | X |  |  |  |  |  |  |  |  |
| Activity 2.14 An evaluation workshop regarding the handbook for auxiliary personnel |  |  |  |  |  |  |  |  | X |  |  |  |  |
| Component Result |  |  |  |  |  |  |  |  |  |  |  |  | C2 R |

| Project Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Component 3 Training of judges, prosecutors And auxiliary personnel of CoA |
| Block A TNA and development training courses |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.1 TNA for judges and prosecutors |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.2 1st meeting on the course Civil Procedure for judges |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.3 2nd meeting on the course Civil Procedure for judges |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.4 3 rd meeting on the course Civil Procedure for judges |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.5 1st meeting on the Course Criminal Procedure for judges and prosecutors of the CoA |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.6 2nd meeting on the Course Criminal Procedure for judges and prosecutors of the CoA |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.7 3rd meeting on the Course Criminal Procedure for judges and prosecutors of the CoA |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.8 Design an an-service training provision for judges and prosecutors of the CoA |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |
| Activity 3.9 TNA for auxiliary personnel |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.10 First meeting of the WG on the course case-flow management for auxiliary personnel of the CoA |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.11 Second meeting of the WG on the course case-flow management for auxiliary personnel of the CoA |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.12 Third meeting of the WG on the course case-flow management for auxiliary personnel of the CoA |  |  |  |  |  |  | Annulled |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.13 Design an in-service training provision for auxiliary personnel of the CoA |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |

| Project Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Block B Train the trainers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.14 First intensive seminar on civil procedure for future trainers of judges |  |  |  |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |
| Activity 3.15 Second intensive seminar on civil procedure for future trainers of judges |  |  |  |  |  |  |  |  |  |  | x |  |  |  |  |  |  |  |
| Activity 3.16 Third intensive seminar on civil procedure for future trainers of judges |  |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |  |  |
| Activity 3.17 First intensive seminar on criminal procedure for future trainers of judges and prosecutors |  |  |  |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |
| Activity 3.18 Second intensive seminar on criminal procedure for future trainers of judges and prosecutors |  |  |  |  |  |  |  |  |  |  | One month delay |  | X |  |  |  |  |  |
| Activity 3.19 Third intensive seminar on criminal procedure for future trainers of judges and prosecutors |  |  |  |  |  |  |  |  |  |  | One month delay |  |  | X |  |  |  |  |
| Activity 3.20 Study visit of the future trainers of judges and prosecutors to the Netherlands |  |  |  |  |  |  |  |  |  |  | x |  |  |  |  |  |  |  |
| Activity 3.21 First intensive training seminar for future trainers of auxiliary personnel |  |  |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |
| Activity 3.22 Second intensive training seminar for future trainers of auxiliary personnel |  |  |  |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |
| Activity 3.23 Third intensive training seminar for future trainers of auxiliary personnel |  |  |  |  |  |  |  |  |  |  | x |  |  |  |  |  |  |  |
| Activity 3.24 Study visit of the future trainers of the auxiliary personnel to Sweden |  |  |  |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |

| Project Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Block C Training programme |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.25 Ten Training seminar for judges dealing with civil cases |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X |  |  |  |
| Activity 3.26 Fourteen seminars for judges dealing with criminal cases and prosecutors |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |
| Activity 3.27 Twelve seminars for auxiliary personnel |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X |  |  |  |
| Activity 3.28 Information gathering and disseminating visit to 3 regions in Turkey. |  |  |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  |  |
| Component Result |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | C3 R |

| Project Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Component 4 Acquainting Turkish officials with Appeal system in EU MS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 4.1 Study visit of Turkish Officials to NL and SE |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component Result |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Recuperation of delays

For all the activities marked in the schedule as delayed by more than three months, provide an explanation of the delay and indicate when the activities will take place.

When drafting this report, we received the message that the publication and dissemination of the speeches and a summary of the discussion at the first Conference for judges and prosecutors of the Court of Cassation (1.3) has been completed and will be printed before the PSC 5 meeting. This means that there are no delays.

Conclusion

There are no delays.

2E. ASSESSMENT

Overall Assessment of progress

General

The project as such is running more or less smoothly. The Train the trainers seminars have been completed, the handbooks are printed and the definite version has been translated. We are now half way the Roll out, which means that most of the problems have been sorted out and that we are working on routine by now. Cooperation is continuing to be good. We are concerned when the Courts of Appeal will actually be established (see 2A).

Activities completed in this quarter

- 3 Train the Trainers seminars (civil and criminal)

- 21 Roll out seminars (civil, criminal and auxiliary staff)

- 1 preparatory meeting for the 2nd conference for Court of Cassation judges and prosecutors

Side letters

In this reporting period eight (8) side letters were submitted to the CFCU in Ankara.

- Side letter 15: Addition of the city of Samsun to the cities of training seminars for judges dealing with civil, and judges and prosecutors dealing with criminal cases and auxiliary personnel. Decreasing the number of seminars in Ankara by one (activities 3.25, 3.26 and 3.27).

- Side letter 16: Addition of MS experts Ms. A. Arpeau and Mr. B. Ahnborg to the pool of experts of activity 3.25. Addition of MS experts Ms A. Ten Bosch-Gerritsen and Ms H. Jonrup (former Nillson) to the pool of experts of activity 3.27

- Side letter 17: Addition of RTA Assistant or Language Assistant to activities 3.25, 3.26 and 3.27 so that she will travel with the RTA to the seminars organized in the regions.

- Side letter 18: Addition of MS Component Leader of Component 1 to activity 1.5

- Side letter 19: Addition of Per Diem and travel expenses of interpreters during activities 3.25, 3.26 and 3.27 in cities other than Istanbul and Ankara.

- Side letter 20: Addition of Ms. Marianne Lejman to the poll of MS experts in activity 3.27 and increasing the SE STE’s in activity 3.27 by one.

- Side letter 21: Addition of six seminars to the training seminars for judges dealing with civil cases and judges and prosecutors dealing with criminal cases to be held in Ankara. Addition of one training seminar for judges dealing with civil cases and judges and prosecutors dealing with criminal cases to be held in Istanbul. Decreasing two training seminars that were planned in Izmir and one seminar that was planned in Erzurum. Cancellation of two seminars that were planned in Samsun and two seminar that were planned in Antalya (Activities 3.25 and 3.26)

- Side letter 22: Increasing the Per Diem budget with one night per expert per seminar for the MS experts who will attend the seminars in Erzurum.

The CFCU approved all above mentioned side letters. However, hard copies of the side letters 20, 21 and 22 shall be submitted to the CFCU shortly.

Conclusion

The assessment of the project is positive.  We are concerned when the Courts of Appeal will actually be established

Issues

Apart from the issues under 2A there are no other specific issues to be mentioned.

Summing up of recommendations and conclusions

Regarding background and assumptions (2A)

- We put question marks with respect to the continued political support to the timely establishment of the Courts of Appeal. We would appreciate it if the Ministry and the High Council could update us during the PSC 5 meeting about the most recent developments and preparatory measures.

Delays (2D and 2E)

- There are no delays.

General and final conclusion (2E)

- In general the assessment is positive. There are concerns regarding the continued support to the timely establishment of the Courts of Appeal.

Attachments:

All activity reports

## Terug naar Ingelse & Cath

# Footnotes

The drafting of this report, 11 April 2007.

Except for the Courts of Appeal in Ankara, Erzurum and Diyarbakır (see the previous IQR’s).However, these buildings will not be ready before the end of 2008. So, in these cities a temporary solution should be found.

+ means completed

According to article 3 of the Workplan month 18, but obviously for the first conference it is month 6 (article 4, under activity 1.7).

Printed end of month 13.

Printed end of month 14.

Printed end of month 12.